VIETNAM FINANCE CASE COMPETITION (VFCC)

Inaugural-Year Proposal

Vietnam Finance Association International (VFAI)

www.vfainternational.org

Executive Summary

The Vietnam Finance Case Competition (VFCC) is a new national English-language undergraduate finance competition organized by VFAI, with mergers and acquisitions as its core theme and valuation, restructuring, financing strategy, and strategic analysis incorporated as adjacent disciplines. In the inaugural year, teams from invited partner universities will submit written advisory memos and Excel models in a national screening round; six to eight finalist teams will then advance to an in-person National Finale in Hanoi. The competition is designed to strengthen analytical, valuation, communication, and decision-making skills among Vietnamese undergraduate students, and to establish a credible annual platform for VFAI to deepen engagement with universities and industry partners.

1. Strategic Positioning

The Vietnam Finance Case Competition (VFCC) is designed to become Vietnam’s flagship undergraduate finance case competition focused on M&A and transaction advisory. It complements existing business and equity research competitions by training students in deal analysis, valuation, financing strategy, financial modeling, and board-level communication, skills that are increasingly important for Vietnam’s evolving financial market.

Unlike broad business case competitions, VFCC is explicitly anchored in finance, with mergers and acquisitions as its thematic core. Each year’s case may also incorporate closely related topics such as capital structure, restructuring, private equity, financing strategy, risk assessment, and post-merger value creation. In this way, VFCC provides a national platform for students interested in investment banking, corporate finance, private equity, consulting, and advisory roles.

The inaugural-year design prioritizes academic credibility, operational feasibility, and sponsor readiness. The first year will use a national screening process followed by a single in-person National Finale in Hanoi. This structure allows VFCC to establish a clear national identity while maintaining quality control in case design, judging, and event execution. In future years, the competition may expand to a multi-region format leading to a National Finale.

2. Strategic Objectives

- Develop undergraduate talent in valuation, M&A analysis, transaction assessment, strategic reasoning, and professional communication.

- Provide students with hands-on experience solving a realistic board-level finance problem using a professional advisory memo format.

- Create a national platform connecting universities, finance professionals, and VFAI around talent development and applied finance education.

- Establish a credible flagship program that can be expanded in future years as participation, sponsorship, and administrative capacity grow.

3. Competition Overview

Official name: Vietnam Finance Case Competition (VFCC).

Organizing body: Vietnam Finance Association International (VFAI).

Inaugural-year format: One national written screening round followed by a single in-person National Finale.

Language: All submissions, slides, and presentations must be in English.

Target participants: Undergraduate students enrolled at invited universities in Vietnam.

Inaugural-year venue: Hanoi, Vietnam.

4. Eligibility and Team Structure

- Participants must be currently enrolled undergraduate students at an invited partner university.

- Each team consists of exactly 4 undergraduate students from the same university.

- Each university may register up to 3 teams.

- Each university must appoint at least one faculty advisor; one advisor may support multiple teams from the same institution.

- Teams may not include graduate students, alumni, or individuals employed full-time in finance or consulting roles.

5. Inaugural-Year Timeline

| Period | Activity |
| --- | --- |
| May-July 2026 | University invitations. Memorandum of Understanding (MOU) signing |
| September 2026 | Competition launch and team registration |
| October 2026 | Workshop series: M&A process, valuation, advisory memo writing, presentation |
| November 2026 | Case release and written submission window |
| Mid December 2026 | In-person National Finale in Hanoi. Awards |
| Post-event | Inaugural-year review |

6. Competition Format — Four Stages

Stage 1 — Launch (September 2026)

Official competition announcement, opening of the registration portal, and confirmation of all participating partner universities and teams.

Stage 2 — Training Workshops (October 2026)

VFAI will organize an optional open workshop series via Zoom for all registered participants. Planned topics include: M&A process and deal logic; valuation and financial modelling; synergies, financing, and deal structure; how to write a professional advisory memo; and presentation and Q&A defense skills.

Stage 3 — Written Screening Round (November 2026)

Teams receive the official case packet and have two weeks to submit: (i) a PDF advisory recommendation memo of 12–15 pages (excluding the cover page and appendices of up to 10 pages), and (ii) a supporting Excel valuation model. All submissions undergo blind review by at least two judges. The top six to eight teams are invited to the National Finale.

Stage 4 — National Finale (Mid December 2026, Hanoi)

Finalist teams present in person in Hanoi. Each team has 15 minutes for their presentation and 15 minutes for Q&A with the judging panel. Judges select the Champion, 1st Runner-up, and 2nd Runner-up. Participating universities will normally bear travel and accommodation costs for their finalist teams.

7. Judging and Evaluation

Written Report Evaluation

Written submissions are evaluated through blind review, with university names removed from judging copies wherever feasible. Each submission is assessed by at least two judges; a third judge is appointed if scores differ by more than 10 points out of 100. The final-round judging panel will be mixed but industry-leaning, combining finance practitioners with academic reviewers.

| Evaluation Dimension | Points | Focus |
| --- | --- | --- |
| Analytical Rigor | 30 | Quality of logic, assumptions, evidence, and recommendation consistency |
| Financial Analysis & Valuation | 30 | Robustness of modelling, valuation methods, pricing logic, and sensitivity analysis |
| Strategic & Transaction Insight | 20 | Assessment of synergies, risks, financing approach, deal structure, and execution |
| Professional Quality of Memo | 20 | Clarity, persuasiveness, structure, and suitability for a board-level advisory memo |
| Total | 100 |  |

Presentation Evaluation

For the finale, judges will additionally assess presentation clarity, command of the analysis, quality of responses during Q&A, and overall professionalism.

| Evaluation Dimension | Points | Focus |
| --- | --- | --- |
| Analytical Rigor | 20 | Quality of logic, assumptions, consistency, depth of analysis |
| Financial Analysis & Valuation | 25 | Robustness of modelling, valuation methods, pricing logic, and sensitivity analysis |
| Strategic & Transaction Insight | 20 | Assessment of synergies, risks, financing approach, deal structure, and execution |
| Recommendation | 10 | Clarity, decisiveness, and board-level relevance of the recommendation. Alignment with analysis and consideration of alternative options. |
| Presentation Delivery | 10 | Clarity, structure, and professionalism of presentation. Ability to communicate complex ideas effectively within time constraints. |
| Q&A | 10 | Ability to respond to questions with clarity and confidence. Depth of understanding of analysis and consistency in defending assumptions and conclusions. |
| Team Coordination | 3 | Balanced participation, teamwork, and smooth coordination among members during presentation and Q&A. |
| Materials & Professionalism | 2 | Quality and clarity of slides and visual materials. Professional formatting and appropriateness for an advisory setting. |
| Total | 100 |  |

Final rankings will be determined based on the overall performance across both the written submission (advisory memo and financial model) and the final presentation.

8. Awards and Prizes

| Champion | 1st Runner-up | 2nd Runner-up |
| --- | --- | --- |
| 50,000,000 VND | 30,000,000 VND | 20,000,000 VND |
| Certificate + Trophy + Cash Prize | Certificate + Trophy + Cash Prize | Certificate + Trophy + Cash Prize |

All finalist teams receive official VFCC certificates of participation. The Champion, 1st Runner-up, and 2nd Runner-up additionally receive trophies and the cash prizes listed above.

9. Governance Structure

Organizing Committee: Responsible for overall management, communications, registration, timeline execution, university coordination, sponsor relations, and final-round logistics.

Academic Committee: Responsible for case development oversight, competition rules, workshop content, judging rubric, blind review procedures, and academic integrity matters.

Official Judging Panel: Responsible for written screening and final-round evaluation. The judging pool will be mixed, weighted toward industry practitioners, and include both Vietnamese and international finance professionals where possible.

10. Academic Integrity and AI-Use Policy

All submitted work must be original. Teams may use AI tools only if use is disclosed via a written declaration specifying which tools were used and for what purpose. Teams remain fully responsible for all analysis, valuation, assumptions, and recommendations submitted under their name. AI tools may not substitute for the team's own judgment.

11. What We Ask of Partner Universities

- Formally nominate up to 3 eligible teams of 4 undergraduate students each.

- Designate at least one faculty advisor to provide general guidance throughout the competition.

- Communicate the VFCC opportunity to students and support participation in the optional VFAI workshop series.

- Ensure finalist teams, if selected, are able to attend the in-person National Finale in Hanoi.

No participation fee will be charged to partner universities in the inaugural year of the competition.

12. Contact and Next Steps

To confirm your institution's participation as an inaugural partner, please contact us via the details below.

For organizations wishing to support the VFCC through sponsorship, we have a separate sponsorship framework with dedicated benefits at each tier. Please contact us for more information.

Email: Dr. Hieu Phan, VFAI President, hieu_phan@uml.edu

Dr. My Nguyen, VFAI Vice President, my.nguyen@rmit.edu.au

Confirmation deadline: TBD

We warmly look forward to welcoming your institution as a founding partner of the inaugural Vietnam Finance Case Competition 2026!